## Summary
Technical Debt Remediation Plan
Plan Parameters
Organization | Example Healthcare Software Co
Planning horizon (years) | 5
Annual budget | 2000000
Annual capacity (days) | 750
Discount rate | 8%
Benefit tail after horizon (years) | 0
Plan Results
Total items | 12
Items remediated within horizon | 11
Items deferred | 1
Total remediation cost (nominal) | 3085000
Remediation cost (NPV) | 2753600.823
Total carry cost under plan (NPV) | 8050886.1696
Total cost if no action (NPV) | 39659039.2037
NPV savings from plan | 28854552.211
NPV savings inside the horizon | 28854552.211

## Year by Year
Year-by-Year Remediation Plan
Year | Items | Total Cost | Effort Days | Budget Used % | Capacity Used %
1 | 10 | 1585000 | 620 | 79.25% | 82.67%
2 | 1 | 1500000 | 360 | 75% | 48%
3 | 0 | 0 | 0 | 0% | 0%
4 | 0 | 0 | 0 | 0% | 0%
5 | 0 | 0 | 0 | 0% | 0%

## All Decisions
All Remediation Decisions
ID | Name | Domain | Year | Priority band | Band rule | Remediation Cost | Effort Days | Carry at Year | NPV Savings | Dependencies | Rationale
OPS-001 | Cloud cost waste - 24/7 dev environments and no RIs | Infrastructure | Year 1 | High | H5: fixing it removes 79% of what doing nothing would cost | 150000 | 60 | 4400000 | 16160937.1545 |  | Funded in year 1; saves $16,161K NPV versus never fixing it.
SEC-001 | SOC 2 Type II expired - access control remediation needed | Security | Year 1 | High | H1: incident probability of 10% a year | 250000 | 90 | 800000 | 5416043.1871 |  | Funded in year 1; saves $5,416K NPV versus never fixing it. Drivers: carry grows 20% a year, 10% annual incident probability, $5.0M incident exposure.
PEOPLE-001 | Key person concentration on platform code | People | Year 1 | High | H1: incident probability of 20% a year | 400000 | 120 | 200000 | 2123372.7901 |  | Funded in year 1; saves $2,123K NPV versus never fixing it. Drivers: carry grows 25% a year, 20% annual incident probability, $2.0M incident exposure.
IP-001 | Missing IP assignments for 12 engineers | Process | Year 1 | High | H1: incident probability of 10% a year | 50000 | 20 | 25000 | 1804915.9375 |  | Funded in year 1; saves $1,805K NPV versus never fixing it. Drivers: 10% annual incident probability, $5.0M incident exposure.
OPS-002 | DR plan never validated | Infrastructure | Year 1 | High | H2: saves 78% of its do-nothing cost, and the cost is growing or incident-driven | 200000 | 90 | 100000 | 1614551.2751 |  | Funded in year 1; saves $1,615K NPV versus never fixing it. Drivers: $8.0M incident exposure.
SEC-002 | Two unremediated High pen test findings | Security | Year 1 | High | H2: saves 78% of its do-nothing cost, and the cost is growing or incident-driven | 80000 | 30 | 50000 | 707886.2365 |  | Funded in year 1; saves $708K NPV versus never fixing it. Drivers: carry grows 15% a year, $2.0M incident exposure.
ARCH-002 | PostgreSQL 11 EOL - upgrade required | Infrastructure | Year 1 | High | H2: saves 59% of its do-nothing cost, and the cost is growing or incident-driven | 200000 | 90 | 50000 | 380285.4058 |  | Funded in year 1; saves $380K NPV versus never fixing it. Drivers: carry grows 30% a year, $1.5M incident exposure.
DATA-002 | Three different MAU definitions across teams | Data | Year 1 | Medium | M1: positive savings with no urgency driver | 120000 | 60 | 80000 | 172232.2126 |  | Funded in year 1; saves $172K NPV versus never fixing it.
DATA-001 | Customer churn calculation bug | Data | Year 1 | High | H5: fixing it removes 54% of what doing nothing would cost | 75000 | 30 | 50000 | 138530.4198 |  | Funded in year 1; saves $139K NPV versus never fixing it.
PROCESS-001 | No DORA metrics tracking | Process | Year 1 | Medium | M1: positive savings with no urgency driver | 60000 | 30 | 30000 | 62169.8688 |  | Funded in year 1; saves $62K NPV versus never fixing it.
ARCH-001 | Multi-tenancy migration abandoned mid-flight | Architecture | Year 2 | High | H3: other items depend on it and it is worth doing early | 1500000 | 360 | 392000 | 273627.723 |  | Funded in year 2; saves $274K NPV versus never fixing it. Its standalone best year is 1, moved to 2 because budget, capacity, or dependencies make that the better portfolio choice. Drivers: $3.0M incident exposure, unblocks ARCH-003.
ARCH-003 | Code modernization to support multi-tenancy | Code | Not funded | Low | H0: fixing costs more than it saves over the horizon | 800000 | 240 | 219615 | 0 | ARCH-001 | Accepted as carry: fixing it costs more than it saves over the 5-year horizon.

## Cost Trajectory
Cost Trajectory: Plan vs No Action
Year | Cost Under Plan | Cost If No Action | Annual Savings
1 | 5187500 | 8547000 | 3359500
2 | 1891000 | 9207750 | 7316750
3 | 211500 | 9954787.5 | 9743287.5
4 | 229650 | 10802286.975 | 10572636.975
5 | 249615 | 11767193.4187 | 11517578.4187